## notes
Any task assigned to a group member must have a deliverable within one week.
Tasks requiring more than one week to fully complete must be broken down into |  |  |  |  | Task Allocation
one week sub-tasks with a partially completed deliverable at the end of a one-week period
This form must be completed with input from all members
Must be completed no later than 6:00pm
All sections of this form are mandatory. (please don't modify this form)
| See Dates |  | Start Date | End Date
Start Date
End Date |  |  | 2019-05-08 | 2019-06-19 | 2019-05-10
Activity | A brief description of the task and what is going to be delivered |  | 2019-07-01 | 2019-08-07 | 2019-07-01
Status | Update "complete" or "in-progress" on the end date
Time required | A reasonable number of minutes to complete the task
Please do not modify the font size on any of the tabs
|  | Always save the worksheet with this tab showing | Items with a status other than "Completed" should be added to the next period.

## May-10
|  | See notes sections | From | To
PRJ666 - Group ___5____ |  | Tasks to be completed | 2019-05-08 | 2019-06-19
Posted On: THU, May.9.2019
Pratik Panchani |  |  |  | Time Required
Start Date | End Date | Activity/Task | Status | (in minutes)
2019-05-08 | 2019-05-09 | Review and find vague part from PRJ566 (Sign In)
2019-05-10 | 2019-05-15 | Sign In (Validation userName)
2019-05-16 | 2019-05-22 | Sign In (Validation password)
2019-05-23 | 2019-05-29 | Sign Out
2019-05-30 | 2019-06-05 | Forget Password (email verification)
2019-06-06 | 2019-06-12 | Forget password (new password)
2019-06-13 | 2019-06-19 | Integrate Back-end with front-end (accounts related)
Arnav Bansal |  |  |  | Time Required
Start Date | End Date | Activity/Task | Status | (in minutes)
2019-05-08 | 2019-05-09 | Review and find vague part from PRJ566 (DB)
2019-05-10 | 2019-05-15 | Install 'React', 'MongoDB', 'node.js'
2019-05-16 | 2019-05-22 | Setup 'node.js' server
2019-05-23 | 2019-05-29 | Setup MongoDB (populate data)
2019-05-30 | 2019-06-05 | Setup MongoDB (Account setup)
2019-06-06 | 2019-06-12 | Set up MongoDB (Create Table)
2019-06-13 | 2019-06-19 | Setup MongoDB (Fetching data with Query)
Gia Tuong Tran |  |  |  | Time Required
Start Date | End Date | Activity/Task | Status | (in minutes)
2019-05-08 | 2019-05-09 | Review and find vague part from PRJ566 (validation)
2019-05-10 | 2019-05-15 | Sign Up (Validation)
2019-05-16 | 2019-05-22 | Sign up (Verification through email) part 1
2019-05-23 | 2019-05-29 | Sign up (Verification through email) part 2
2019-05-30 | 2019-06-05 | Decide Password Algorithm
2019-06-06 | 2019-06-12 | Password Encription
2019-06-13 | 2019-06-19 | Integrate Back-end with front-end (validation and verification)
YoungMin Ko |  |  |  | Time Required
Start Date | End Date | Activity/Task | Status | (in minutes)
2019-05-08 | 2019-05-09 | Review and find vague part from PRJ566 (UI)
2019-05-10 | 2019-05-15 | Main Page UI Design
2019-05-16 | 2019-05-22 | Main Page (navigation bar, category)
2019-05-23 | 2019-05-29 | Main Page (display quote, display username(author))
2019-05-30 | 2019-06-05 | Main Page (date of upload)
2019-06-06 | 2019-06-12 | Main Page (ratings)
2019-06-13 | 2019-06-19 | Main Page (reporting dialog box)
Member Name |  |  |  | Time Required
Start Date | End Date | Activity/Task | Status | (in minutes)

## Jul-01
|  | See notes sections | From | To
PRJ666 - Group _______ |  | Tasks to be completed | 2019-07-01 | 2019-08-07
Posted On:
Member Name |  |  |  | Time Required
Start Date | End Date | Activity/Task | Status | (in minutes)
Member Name |  |  |  | Time Required
Start Date | End Date | Activity/Task | Status | (in minutes)
Member Name |  |  |  | Time Required
Start Date | End Date | Activity/Task | Status | (in minutes)
Member Name |  |  |  | Time Required
Start Date | End Date | Activity/Task | Status | (in minutes)
Member Name |  |  |  | Time Required
Start Date | End Date | Activity/Task | Status | (in minutes)